## RACI
Sparks Motor New Electric Car Launch RACI Matrix SparkE
Teams Deliverables | Marketing Team | Manufacturing Team | Sales Team | Dealerships | Regulatory Bodies | Executive Team
Develop Marketing Strategy | R | I | I | C | I | I
Design and Manufacture Car | I | R | I | I | I | I
Create Marketing Materials | R | C | I | I | I | I | R | Responsible - Who perform the task
Conduct Market Research | R | I | R | R | I | I | A | Accountable - Who sings off
Train Dealership Staff | R | I | R | A | I | I | C | Consultant - Who provider expertise
Launch Event Planning | A | I | C | C | I | I | I | Inform - Who is kept inform
Monitor Sales Performance | R | I | R | A | I | I
Ensure Regulatory Compliance | I | A | I | I | A | I
Review and Approve Budget | A | I | I | I | I | A
Address Customer Complaints | I | I | C | R | I

## Register
Sparks Motor New Electric Car Launch Stakeholder Register SparkE
Stakeholder | Role | Interest | Influence | Expectations | Engagement Level
Executive Team | Decision-makers | High | High | Financial success, market leadership | Direct involvement, regular updates
Marketing Team | Marketing professionals | High | Moderate | Successful product launch, effective marketing | Direct involvement, collaboration with other teams
Sales Team | Sales professionals | High | Moderate | Achieving sales targets, product knowledge | Direct involvement, collaboration with marketing
Dealership | Business partners | High | Moderate | Product availability, marketing support | Regular communication, training sessions
Customers | Potential buyers | High | Low-Moderate | Quality product, transparent information | Marketing events, customer surveys
Regulatory Bodies | Compliance officers | Moderate | High | Adherence to safety and environmental standards | Regular reporting, compliance updates
Manufacturing Team | Production experts | Moderate | High | Efficient production, quality control | Direct involvement, regular updates
Employees | Internal staff | Moderate | Low | Job security, company success | Internal communications, employee engagement programs

## Grid
Sparks Motor New Electric Car Launch Power and Interest Grid SparkE
Interest
P
o
w
e
r
High
High
Low
High Power , Low Interest
High Power , High Interest
Low Power , High Interest
Low Power , Low Interest
Manufacturing Team
Sales Team
Regulatory Bodies
Executive Team
Marketing Team
Dealearship
Customer
Emplyoees
Community Groups